## Issues List
IssueID | Date Entered | Entered By | Description | Issue Type | Priority | Resource | Status | Release | Resolution Plan | Test Procedure
SUD_001 | 2023-05-16 | JDL | fullassessment.py Pytest validation with new folder structure | Enhancement | High | JD | Complete | 2023-05-16 | Passes 30 tests in 5/16/23 test_fullassess.py | pytest test_fullassess.py all tests
Issue_001 | 2023-11-20 | JDL | Scenario Model Refresh does not insert comment if formula syntax error (trying to put comment on rngModel all columns instead of just variable name cell) | Bug | High |  | Complete | 2023-11-21 | Modification to mdlRow.WriteRowFormula()
Issue_002 | 2023-11-20 | JDL | Scenario Model Refresh does not show error message dialog if formula syntax error | Bug | High |  |  | 2023-11-21
Issue_003 | 2023-11-21 | JDL | Modifications needed to ErrorHandling Class in course of fixing Issue_001 and _002 | Enhancement |  |  | Complete |  | See notes in ErrorHandling class

## Lists
ListPriority | ListTypes | ListStatus | ListResource
Critical | Bug | Complete | JD
High | Enhancement | In Progress | Other
Moderate | Analysis | Wish List
Low | Maintainability

## XLStepsSettings (hidden)
Type | txtval | boolean1 | boolean2
ShtNameFrm | Issues List | TRUE | TRUE
cBoxAppShtName |  | FALSE

## ExcelSteps
Sheet | Column | Step | Formula/List Name/Sort-by | After or End Column | Keep Formulas | Comment | Number Format | Width
Issues List | Description | Col_Format | [5 empty] | 35
Issues List | Resolution Plan | Col_Format | [5 empty] | 35
Issues List | Priority | Col_Dropdown | ListPriority |  |  |  |  | 10
Issues List | Resource | Col_Dropdown | ListResource |  |  |  |  | 10
Issues List | Issue Type | Col_Dropdown | ListTypes |  |  |  |  | 10
Issues List | Status | Col_Dropdown | ListStatus |  |  |  |  | 10